## Financial Proj
Housing | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022
Projected Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275002 | 304043 | 306243 | 307343 | 307343 | 307343 | 348743 | 348743 | 348743 | 348743 | 348743 | 348743 | 443000 | 478783 | 478783 | 478783 | 642113.89 | 643525.64 | 643525.64 | 741216.43 | 862966.43 | 862966.43 | 862966.43 | 862966.43 | 862966.43 | 862966.43 | 871467.83 | 879969.23 | 888470.63 | 896972.03 | 905473.43 | 905473.43 | 905473.43
Quarterly Projection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275002 | 29041 | 2200 | 1100 | 0 | 0 | 41400 | 0 | 0 | 0 | 0 | 0 | 94257 | 35783 | 0 | 0 | 163330.89 | 1411.75 | 0 | 97690.79 | 121750 | 0 | 0 | 0 | 0 | 0 | 8501.4 | 8501.4 | 8501.4 | 8501.4 | 8501.4 | 0 | 0
Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275002.32 | 304043.69 | 306243.69 | 307343.69 | 307343.69 | 307343.69 | 348743.69 | 348743.69 | 348743.69 | 348743.69 | 348743.69 | 348743.69 | 443000.69 | 478783.71 | 478783.71 | 478783.71 | 642114.6 | 643526.35 | 643526.35 | 741217.14 | 862967.14 | 862967.14 | 862967.14 | 862967.14 | 862967.14 | 862967.14 | 862967.14 | 862967.14 | 862967.14 | 862967.14 | 862967.14 | 862967.14 | 862967.14
Actual Quarterly Expend (from QPRs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275002.32 | 29041.37 | 2200 | 1100 | 0 | 0 | 41400 | 0 | 0 | 0 | 0 | 0 | 94257 | 35783.02 | 0 | 0 | 163330.89 | 1411.75 | 0 | 97690.79 | 121750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Projects | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022
Projected Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99593 | 157286 | 209659 | 574741 | 1148038 | 2622147 | 2830687 | 2830687 | 2984837 | 3541383 | 4142058 | 4352664 | 4512504 | 4512504 | 4638946 | 4694047 | 4694047 | 5037974 | 5051518 | 5051518 | 5051518 | 5051518 | 4990269 | 5262963 | 5746421.85 | 6229880.7 | 6713339.55 | 7196798.4 | 7680257.25 | 7680257.25 | 7680257.25
Quarterly Projection | [7 empty] | 0 | 0 | 0 | 99593 | 57693 | 52373 | 365082 | 573297 | 1474109 | 208540 | 0 | 154150 | 556546 | 600675 | 210606 | 159840 | 0 | 126442 | 55101 | 0 | 343927 | 13544 | 0 | 0 | 0 | -61249 | 272694 | 483458.85 | 483458.85 | 483458.85 | 483458.85 | 483458.85 | 0 | 0
Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99592.89 | 157286.27 | 209659.14 | 574740.64 | 1148038 | 2622147.11 | 2830686.77 | 2830686.77 | 2984836.68 | 3541382.2 | 4142056.9 | 4352662.94 | 4512502.91 | 4512502.91 | 4638945.35 | 4694046.33 | 4694046.33 | 5037973.28 | 5051517.08 | 5051517.08 | 5051517.08 | 5051517.08 | 4990268.46 | 5262962.04 | 5262962.04 | 5262962.04 | 5262962.04 | 5262962.04 | 5262962.04 | 5262962.04 | 5262962.04
Actual Quarterly Expend (from QPRs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99592.89 | 57693.38 | 52372.87 | 365081.5 | 573297.36 | 1474109.11 | 208539.66 | 0 | 154149.91 | 556545.52 | 600674.7 | 210606.04 | 159839.97 | 0 | 126442.44 | 55100.98 | 0 | 343926.95 | 13543.8 | 0 | 0 | 0 | -61248.62 | 272693.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning & Admin | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022
Projected Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100845 | 100845 | 116108 | 116108 | 116108 | 116108 | 127613 | 127613 | 127613 | 127613 | 127613 | 147953 | 147953 | 181801 | 181801 | 181880 | 181880 | 199060.06 | 232764.04 | 234573.98 | 234573.98 | 234573.98 | 234573.98 | 237625.95 | 237625.95 | 259912.75 | 282199.55 | 304486.35 | 326773.15 | 349059.95 | 349059.95 | 349059.95
Quarterly Projection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100845 | 0 | 15263 | 0 | 0 | 0 | 11505 | 0 | 0 | 0 | 0 | 20340 | 0 | 33848 | 0 | 79 | 0 | 17180.06 | 33703.98 | 1809.94 | 0 | 0 | 0 | 3051.97 | 0 | 22286.8 | 22286.8 | 22286.8 | 22286.8 | 22286.8 | 0 | 0
Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100845.15 | 100845.15 | 116107.98 | 116107.98 | 116107.98 | 116107.98 | 127613.46 | 127613.46 | 127613.46 | 127613.46 | 127613.46 | 147953.95 | 147953.95 | 181801.74 | 181801.74 | 181880.94 | 181880.94 | 199061 | 232764.98 | 234574.92 | 234574.92 | 234574.92 | 234574.92 | 237626.89 | 237626.89 | 237626.89 | 237626.89 | 237626.89 | 237626.89 | 237626.89 | 237626.89 | 237626.89
Actual Quarterly Expend (from QPRs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100845.15 | 0 | 15262.83 | 0 | 0 | 0 | 11505.48 | 0 | 0 | 0 | 0 | 20340.49 | 0 | 33847.79 | 0 | 79.2 | 0 | 17180.06 | 33703.98 | 1809.94 | 0 | 0 | 0 | 3051.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expenditures | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022
Projected Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275002 | 404888 | 506681 | 580737 | 633110 | 998192 | 1612889 | 3098503 | 3307043 | 3307043 | 3461193 | 4017739 | 4733011 | 4979400 | 5173088 | 5173088 | 5462939.89 | 5519452.64 | 5536632.7 | 6011954.47 | 6149058.41 | 6149058.41 | 6149058.41 | 6149058.41 | 6090861.38 | 6363555.38 | 6877802.43 | 7392049.48 | 7906296.53 | 8420543.58 | 8934790.63 | 8934790.63 | 8934790.63
Quarterly Projection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275002 | 129886 | 101793 | 74056 | 52373 | 365082 | 614697 | 1485614 | 208540 | 0 | 154150 | 556546 | 715272 | 246389 | 193688 | 0 | 289851.89 | 56512.75 | 17180.06 | 475321.77 | 137103.94 | 0 | 0 | 0 | -58197.03 | 272694 | 514247.05 | 514247.05 | 514247.05 | 514247.05 | 514247.05 | 0 | 0
Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275002.32 | 404888.84 | 506681.73 | 580737.94 | 633110.81 | 998192.31 | 1612889.67 | 3098504.26 | 3307043.92 | 3307043.92 | 3461193.83 | 4017739.35 | 4733011.54 | 4979400.6 | 5173088.36 | 5173088.36 | 5462940.89 | 5519453.62 | 5536633.68 | 6011955.4 | 6149059.14 | 6149059.14 | 6149059.14 | 6149059.14 | 6090862.49 | 6363556.07 | 6363556.07 | 6363556.07 | 6363556.07 | 6363556.07 | 6363556.07 | 6363556.07 | 0
Actual Quarterly Expend (from QPRs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275002.32 | 129886.52 | 101792.89 | 74056.21 | 52372.87 | 365081.5 | 614697.36 | 1485614.59 | 208539.66 | 0 | 154149.91 | 556545.52 | 715272.19 | 246389.06 | 193687.76 | 0 | 289852.53 | 56512.73 | 17180.06 | 475321.72 | 137103.74 | 0 | 0 | 0 | -58196.65 | 272693.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Performance Proj
Demolition & Debris Removal | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019
Projected Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 15 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
# of Housing Units (Quarterly Projection) | 0 | [6 empty] | 5 | 10 | 5
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Housing Units (Populated from QPR Reporting) | 0
Home Purchase | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019
Projected Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
# of Housing Units (Quarterly Projection) | 0 | [12 empty] | 1
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Housing Units (Populated from QPR Reporting) | 0
Safe Rooms | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019
Projected Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
# of Housing Units (Quarterly Projection) | 0 | [9 empty] | 1 | 1 | 1
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Housing Units (Populated from QPR Reporting) | 0
Residential Rehab and Reconstruction | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019
Projected Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 11 | 16 | 21 | 25 | 28 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
# of Housing Units (Quarterly Projection) | 0 | [5 empty] | 0 | 1 | 5 | 5 | 5 | 5 | 4 | 3 | 2
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Housing Units (Populated from QPR Reporting) | 0
Public Facilities | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019
Projected Facilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
# of Public Facilities (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Facilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Public Facilities (Populated from QPR Reporting) | 0
Quarterly Projections by Activity Type:
Acquisition, construction,reconstruction of public facilities
# of Public Facilities | 0 | [8 empty] | 1 | 1 | 1
Construction/reconstruction of water lift stations
# of Public Facilities | 0
Construction/reconstruction of water/sewer lines or systems
# of Public Facilities | 0 | [10 empty] | 3
Dike/dam/stream-river bank repairs
# of Public Facilities | 0
Rehabilitation/reconstruction of public facilities
# of Public Facilities | 0
Economic Development | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019
Projected Jobs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Jobs Created/Retained (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Jobs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Jobs Created/Retained (Populated from QPR Reporting) | 0
# of Permanent Jobs Created | 0
# of Permanent Jobs Retained | 0
Public Infrastructure | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019
Projected Linear Feet of Public Improvements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529
# of Linear Feet of Public Improvements (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Linear Feet of Public Improvements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Linear Feet of Public Improvements (Populated from QPR Reporting) | 0
Quarterly Projections by Activity Type:
Construction/reconstruction of water/sewer lines or systems
# of Linear Feet of Public Improvements | 0 | [10 empty] | 6529
Dike/dam/stream-river bank repairs
# of Linear Feet of Public Improvements | 0
Rehabilitation/reconstruction of a public improvement
# of Linear Feet of Public Improvements | 0